## Project Information
I Reiquirements.
Hệ thống phòng khám tư nhân “Healthy system” là 1 website cho phép bệnh nhân hoặc người muốn xem thông tin và tìm hiểu thông tin về phòng khám cũng như đặt lịch khám bệnh cho bệnh nhân như sau: - Cho phép người dùng vào xem các thông tin về phòng khám. Ví dụ, thông tin các chuyên môn khám, thông tin bác sỹ, thông tin trang thiết bị,… - Cho phép người dùng đăng ký lịch khám trực tuyến bằng cách chọn bác sĩ khám, chọn ngày giờ khám bệnh - Cho phép người dùng tạo tài khoản để xem lại các thông tin về lịch sử bệnh cũng như quá trình điều trị của mình - Cho phép người dùng thay đổi lịch hẹn khi đã đặt lịch (thời gian trước khi khám 2 tiếng) - Cho phép người dùng gọi tới đường dây nóng của phòng khám để đặt câu hỏi và nhận tư vấn - Cho phép người dùng đánh giá về bác sĩ cũng như các dịch vụ của phòng khám Ngoài ra cần phải xấy dựng trang website adimn để quản lí các đơn đặt khám của bệnh nhân, và thay đổi lịch cho bệnh nhân(nếu bệnh nhân có nhu cầu), liên hệ bệnh nhân khi cần.

## Team
TEAM DEVELOPMENT STRUCTURE
No. | Name | Account | Roles | DateStart | Date End
1 | Phan Lâm Chí Thông | thongphan | Product Owner | 2023-03-02
2 | Phạm Thái Nguyên | nguyenpham | ScrumMaster | 2023-03-02
3 | Đàm Huy Dũng | dungdam | Team Lead | 2023-03-02
4 | Nguyễn Vũ Thành Đạt | datnguyen | Dev | 2023-03-02

## Product Backlog
HEALTHY CLINICS PROJECT - PRODUCT BACKLOG
Story ID | Story Name | Points
71
Actor: Guest
1 | View HomePage | 4
2 | View Doctor list | 4
3 | View Doctor details | 4
4 | View Clinics Information | 4
5 | View services | 4
6 | Registration | 4
7 | Chat with Customer Sevice | 4
Actor: User(Customer-Doctor)
6 | Registration | 4
8 | Login | 1
13 | Logout | 1
9 | Booking | 5
10 | Booking Management (View, Cancel request) | 5
11 | View booking progress | 3
12 | View price | 4
Actor: Booking Manager
8 | Login | 1
13 | Logout | 1
14 | View New Booking | 3
15 | Booking Management (View, Edit, Update) | 4
Actor: Administration
16 | User Management | 5
17 | Updates Page | 4
8 | Login | 1
13 | Logout | 1

## Sprint Backlog
HEALTHY CLINICS PROJECT - SPRINT BACKLOG
Sprint 1
Story ID | Story Name: Create layout & Create Database | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
30
1 | HomePage | 4 | Thong, Dat | 2023-03-04 | 2023-03-15
2 | Doctor list | 4 | Thong, Dat | 2023-03-04 | 2023-03-15
3 | Doctor details | 4 | Thong, Dat | 2023-03-04 | 2023-03-15
4 | Clinics Information | 4 | Thong, Dat | 2023-03-04 | 2023-03-15
5 | View services | 4 | Thong, Dat | 2023-03-04 | 2023-03-15
6 | Registration | 4 | Dung,Nguyen | 2023-03-04 | 2023-03-15
7 | View price | 4 | Thong, Dat | 2023-03-04 | 2023-03-15
8 | Login | 1 | Dung,Nguyen | 2023-03-04 | 2023-03-15
9 | Logout | 1 | Dung,Nguyen | 2023-03-04 | 2023-03-15
Sprint 2
Story ID | Story Name: Functions | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
16
10 | Booking(Only Customer) | 5 | Dung,Nguyen | 2023-03-16 | 2023-03-30
11 | Booking Management (View, Cancel request) | 5 | Dung,Nguyen | 2023-03-16 | 2023-03-30
12 | View booking progress | 3 | Thong, Dat | 2023-03-16 | 2023-03-30
13 | Chat with Customer Sevice | 3 | Dung,Nguyen | 2023-03-16 | 2023-03-30
Sprint 3
Story ID | Story Name: Manage | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
7
14 | View New Booking | 3 | Thong, Dat | 2023-04-01 | 2023-04-15
15 | Booking Management (View, Edit, Update) | 4 | Dung,Nguyen | 2023-04-01 | 2023-04-15
Sprint 4
Story ID | Story Name: Adminstration | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
9
16 | User Management | 5 | Thong, Nguyen | 2023-04-16 | 2023-04-30
17 | Updates Page | 4 | Dung, Dat | 2023-04-16 | 2023-04-30